## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Fundamentals and Prequsites to work with Project | MUST HAVE | W3 schools | kamakshi kamalika | 3- Completed
|  | 2 | Understanding the Project, Project environment setup and Database integration | MUST HAVE | vs code | kamakshi kamalika | 3- Completed
|  | 3 | Parallel Text Handling | MUST HAVE | Jupyter notebook | kamakshi kamalika | 3- Completed
|  | 4 | Paralelle text Loading, Breaking, Grouping, Searching & Integration | MUST HAVE | vs code | kamakshi kamalika | 3- Completed
Note on F1: ====== ID#AAABs5CmnRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
w
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 45948 | 45949 | 45950 | 45951 | 45952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Fundamentals and Prequsites to work with project | sep 18th | 2nd Oct | Akurathi Kamakshi kamalika | Strengthening python foundations | Done |  | Intoduction of work flow | Intro of python | Sample programs | Brief view of various python platforms | Python Overview | Syntax fundamentals | loops and Conditions | practiced loops | String operations | Functions Overview | Mastering Basics of functions | Understanding function arguments | Python modules | Basics of OOPs
2 |  | Understanding the Project, Project environment setup and Database integration | 3rd Oct | 17th Oct | Akurathi kamakshi kamalika | Learning Multi-Processing and Project Understanding | Done |  | OOPS | oops hands on | Some more problems | Modular Python with Packages | Concept of Multiprocessing | Multiprocessing & Pipe | practiced problems on multi processing | project introduction | Presented Project like an interview | Environment setup and basics of sqlite3 | Completed Sqlite3 | prepared for project interview | learned Multi-tasking in python | practiced Muti-tasking
|  | Parallel text handling | 18th Oct | 1st Nov | Akurathi kamakshi kamalika | practicing workflows and establishing the core project setup | Done |  | project set up | Revised notes | Go thorugh all problems | Introduction of multi tasking | Learned Thread pool Executer | Practiced both multi tasking and thread pool Executer | Learned Regular Expressions | Research about Generator | Practiced some common patterns | Text handling | Practiced text handling | Implemented regex | Completed rule Based Tagging | Started project Hands on
|  | parallel text loading,breaking and grouping | 2nd Nov | 16th Nov | Akurathi kamakshi kamalika | Started project | Done |  | overview of project | Continued Hands on Implementation | Text Breaking and grouping | hands-on | completed text breaking and grouping | Milestone2 code walkthrough | revised notes | Text breaking and grouping | performance optimization | Implementation of code | discussed upcoming plans | SMTP Library | Implementing programs | Revised some concepts
3 | [8 empty] | Day 1: 2025-10-18; Day 2: 2025-10-19; Day 3: 2025-10-20; Day 4: 2025-10-21; Day 5: 2025-10-22
3
3
3
3
3
3
3
3
3
3
3
3
3
4
4
4
4
4
4
4
4
4
4
4
4
4
4
Note on D2: ====== ID#AAABs5CmnRY Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs5CmnQ4 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs5CmnRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs5CmnQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs5CmnQg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs5CmnQk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs5CmnRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs5CmnRU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs5CmnRI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs5CmnQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs5CmnQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs5CmnQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs5CmnRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs5CmnRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs5CmnQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs5CmnRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs5CmnRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7